| Goal #2: To define our brand and inter-relationship with AHRC and its affiliates. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Chair: Mary McNamara Committee: Roz Goldmacher, Carolyn Ciatto, Chris O’Connor, Zania Ledwidge, Maryann Dellova, George Bauer, Nicole Zerillo |  |  |  |  |  |
| Tasks | Responsible | Start | Resources Required | Outcomes/Measures | Comments/Improvements |
| Discovery 2.1 Develop a report, by end of September 2017, sharing data needed to make an assessment of Citizens’ brand and clarify its role within AHRC’s brand family | Mary McNamara; Full Committee, as assigned | 4/17 | Time of the Committee | - Present findings in a report to Strategic Planning leadership. Complete. | - Additional report submitted to highlight Citizens’ existing programs and services, as well as help define organization’s competitive advantage. Complete. |
| Development of Brand Strategy 2.2 Develop a brand strategy, by end of April 2018, with recommendations for sustainable development of the brand Development of Brand Strategy 2.2 Develop a brand strategy, by end of April 2018, with recommendations for sustainable development of the brand Development of Brand Strategy 2.2 Develop a brand strategy, by end of April 2018, with recommendations for sustainable development of the brand Development of Brand Strategy 2.2 Develop a brand strategy, by end of April 2018, with recommendations for sustainable development of the brand Development of Brand Strategy 2.2 Develop a brand strategy, by end of April 2018, with recommendations for sustainable development of the brand | Mary McNamara; Full Committee, as assigned | 12/17 | Time of the Committee | - Evaluate data from Discovery Phase (2.1) on Citizens’ brand assets and placement within the AHRC brand family. See submitted reports. - Present report of proposed strategy, tactical roll-out plan and budget to Strategic Planning leadership. | - Strategic approach updated to align with CQL goals - On track, for end of April, to update brand elements and strategy to: - Propose unique corporate identity, brand story, messaging for each service area, images and shared language - Increase awareness of Camp Loyaltown as a program of Citizens through visual cues, messaging and social media - Clarify Citizens’ program from AHRC’s: - Plan actionable organizational chart highlighting roles/responsibilities and points of contact - To be made available on new intranet, Connect - To keep digital chart up to date, plan how to maintain - Plan Citizens “welcome” toolkit to help inform new program participants and families on available services and points of contact - Increase marketing and media opportunities through planning of cross-departmental content-gathering process, including: - Concise online content collection form - Content sharing across departments who produce publications (i.e. Community Resources, HR and Compass): - Currently testing content-sharing tools, including Asana, Slack and AHRC’s intranet, Connect, to ensure all content can simultaneously receive the same stories, review and track when/how used - Frequently Asked Questions (FAQs) document on development of marketing materials and media process - In-person Q&A/ brainstorming sessions - For consistent marketing materials, make available to all employees: - Email signature and confidentiality/business disclosure footer - Progress made on email template for all staff in family of organizations; third draft in process - User-friendly portal and instructions to be developed - Ready-to-order and approved collateral through printer/Purchasing Department - Style guide to create consistency on writing, editing and proofing conventions - Document to describe Community Resources’ scope of services (e.g., development of forms, emails, brochures, marketing copy) - Policies and procedures for group communications: - Message development and distribution process - Timeline - Stakeholders - Viability and/or role of PPC network in this updated system - Ongoing strategy meetings held with: - Citizens’ management team to finalize branding materials, including mission poster and CQL video showcasing person-centered excellence and brand interrelationship - Self Direction and POM leaders to discuss success stories to feature in media and marketing - Family Support Services to highlight staff and ongoing programming - HR to develop communications for recruitment campaigns - ComeUnity Recreation for updated materials and communications aligning with Citizens branding - Central Enrollment to create more accessible “doorway” to services on website, as well as digital organizational chart highlighting roles/responsibilities and points of contact - Camp Loyaltown team to discuss year-round support, ranging from recruitment for staff to ongoing respite programs - Programs and Services to communicate MSC change-over in 2018 - Community Living Services to plan the second phase of #DSPsRock recognition campaign for summer - Community Resources Events team to work on 2018 events - Review AHRC Walk materials to better position Citizens in 2018 - Community Resources Volunteer Coordinator to better position Citizens’ volunteering opportunities |
| Implementation 2.3 Implementation of plan, by end of August 2018, create and roll out updated brand utilizing storytelling components to resonate with stakeholders Implementation 2.3 Implementation of plan, by end of August 2018, create and roll out updated brand utilizing storytelling components to resonate with stakeholders | Mary McNamara; Full Committee, as assigned | 4/18 | Time of the Committee | - Update submitted branding with Strategic Planning leadership recommendations - Create brand identity guidelines including organizational access to materials bank - Leverage wealth prospecting software to increase fundraising - Roll out updated branding - Begin implementation of integrated content marketing plan for building brand awareness of specific programs among key audiences - Mobilize brand ambassadors to respond to timely topics to create features - Develop and distribute guidelines for staff to share their contributions to the organization’s mission through newsletters, editorial schedule, etc. - Begin implementation of monitoring and measurement of marketing and communications initiatives | - Community Resources finalized branding elements: - 2018 stationary - Logo featuring Camp Loyaltown as a program of Citizens Options Unlimited - Email wrapper/ header featuring Citizens and Camp Loyaltown branding - Template for mission poster - Unique images to be captured for poster (Q2), then finalized - Progress made on email template for all staff in family of organizations; third draft in process - Email footer for business confidentiality/disclosures in process - CQL video completed and presented at meetings to showcase person-centered excellence and brand interrelationship through testimonials - Campaigns underway for: - MSC transition - DSP Recruitment - Camp Loyaltown promotions in process: - Fundraising event, Splash Bash with JP Morgan on May 23 - Media pitch on intern with autism from NYIT’s VIP program working in Camp Loyaltown office - Online campaign to double number of Facebook followers due to channel’s success in recruiting counselors - Advertising placements: - Long Island Business News’ Book of Lists (submitted) - SUNY Old Westbury Athletics calendar for ComeUnity Sports volunteer opportunities - Long Island Special Child website directory for Camp Loyaltown - Advocacy issues, including Medicaid and #bfair2directcare, cross-promoted as part of AHRC family of organizations - Volunteer online portal is operational with more accessible training schedule |
| 2.4 On a quarterly basis, report on progress of newly developed brand assets | Mary McNamara; Full Committee, as assigned | 4/18 | Time of the Committee | - Measurement report to inform, refine or expand existing recommendations |  |